## Sheet1
Date | Project number | Type | Status | Delayed | Issues | Project cost | Category | Classification
2022-10-29 | P/2021/1 | Complex | On Hold | Y | rescoping and new agency will be aligned | 153400 | Custom Website and Application Development | Strong
2022-10-29 | P/2021/2 | Marketing | On Hold | N | Technical | 17700 | Custom Social Media Marketing | Strong
2022-10-31 | P/2021/3 | Websites | Delivered | Y | Delay in content and approvals | 40120 | Custom Website Development | Strong
2022-10-31 | P/2021/4 | Websites | Running | N |  | 41300 | Custom Mobile App Development | Strong
2022-11-01 | P/2021/5 | Complex | Running | Y | Client | 82600 | Custom Videography | Strong
2022-11-01 | P/2021/6 | Complex | Escalation | Y | Delay in design & lack of domain understanding | 330400 | Custom Website and Application Development | Strong
2022-11-02 | P/2021/7 | Websites | Delivered | Y | Client | 15340 | Custom Website Development | Strong
2022-11-03 | P/2021/8 | Marketing | Running | N |  | 70796.64 | Custom Social Media Management | Strong
2022-11-03 | P/2021/9 | Marketing | Running | N |  | 659999 | Custom Performance Marketing | Strong
2022-11-03 | P/2021/10 | Simple Apps | Running | N |  | 169491 | Custom Web Mobile Application Development | Strong
2022-11-07 | P/2021/11 | Simple Apps | Delivered | N |  | 44802.24 | Custom Website Development | Strong
2022-11-07 | P/2021/12 | Websites | On Hold | N |  | 20060 | single vendor e- commerce website | Strong
2022-11-07 | P/2021/13 | Websites | Running | Y | Client | 40993.2 | Custom Website Development | Strong
2022-11-07 | P/2021/14 | Websites | Running | N | Client | 35400 | Custom Website AMC | Strong
2022-11-08 | P/2021/15 | Marketing | Running | N | Client, SM(Add sections in videos) | 10200 | Emailer Template Creation | Strong
2022-11-08 | P/2021/16 | Simple Apps | Running | N | Client,SM | 59000 | Custom Multi Vendor Booking Application | Strong
2022-11-08 | P/2021/17 | Simple Apps | Running | N | OIE, SM | 64900 | Custom Multi Vendor Application | Strong
2022-11-09 | P/2021/18 | Websites | Running | N | Client | 350460 | Tapan Ray Chowdhury Custom Website | Strong
2022-11-09 | P/2021/19 | Marketing | Running | N | Client, SM | 4720 | Custom Content Writing | Strong
2022-11-09 | P/2021/20 | Marketing | Running | N | Client | 177000 | Social media marketing | Strong
- | P/2021/21 | Websites | Running | N |  | 67850 | Custom Single Vendor E-Commerce Website | Strong
2022-11-10 | P/2021/22 | Simple Apps | Running | N |  | 160000.92 | Custom Application Development | Strong
2022-11-11 | P/2021/23 | Websites | Running | Y | Client | 67260 | Multi-Vendor e-commerce | Strong
2022-11-11 | P/2021/24 | Marketing | Running | N | Client,OIE | 141600 | Custom SEO | Strong
2022-11-11 | P/2021/25 | Simple Apps | Running | N | SM, OIE | 129800 | Custom Application Development | Strong
2022-11-14 | P/2021/26 | Complex | Running | N |  | 944000 | ERP | Strong
2022-11-14 | P/2021/27 | Complex | Running | N |  | 36580 | ERP | Strong
2022-11-17 | P/2021/28 | Websites | Running | N | SM(More post & High ad budget) | 21830 | Product Listing | Strong
2022-11-17 | P/2021/29 | Simple Apps | Delivered | N |  | 45000 | Custom Login Page Development | Strong
2022-11-18 | P/2021/30 | Marketing | Running | N | SM(wanted shopify & not woocommerce) | 35400 | Custom Social Media Management | Strong
2022-11-22 | P/2021/31 | Marketing | Running | N | OIE, Technical | 9440 | Social Media Advertising | Strong
2022-11-22 | P/2021/32 | Websites | Running | Y |  | 27140 | Custom Website Development and Content | Strong
- | P/2021/33 | Marketing | Running | N | OIE, SM | ₹41,300 | Social Media Advertising | Strong
2022-11-22 | P/2021/34 | Simple Apps | Running | N | SM(ship rocket integration,tracking facility in website) | 59000 | Custom Hybrid Application Development | Strong
2022-11-22 | P/2021/35 | Marketing | Running | N | SM | 247800 | Custom SEO and SMM | Strong
2022-11-23 | P/2021/36 | Marketing | Running | N | Client | 33040 | Ecommerce Marketplace Listing and Advertising | Strong
2022-11-23 | P/2021/37 | Marketing | Running | N | SM | 10620 | Ecommerce Marketplace Listing and Advertising | Strong
2022-11-24 | P/2021/38 | Marketing | On Hold | N | SM(whtasapp integration, & social media ) | 35400 | Performance Marketing | Strong
2022-11-25 | P/2021/39 | Simple Apps | Running | N | Technical, OIE, SM(tech stack, video feature addition) | 1034860 | Custom Application Development | Strong
2022-11-25 | P/2021/40 | Simple Apps | Running | N |  | 450000 | Custom Application Development | Strong
2022-11-26 | P/2021/41 | Websites | Running | N |  | 53808 |  | Strong
2022-11-26 | P/2021/42 | Websites | Running | N | SM | 59606 | Multi vendor website development - lease listing | Strong
2022-11-29 | P/2021/43 | Simple Apps | Running | N | Client | 123900 | Ecommerce Application Development | Strong
2022-11-30 | P/2021/44 | Websites | Running | N | Technical,SM-Data Migration | 27140 | Informative Website | Strong
2022-11-30 | P/2021/45 | Marketing | Running | N | OIE, SM | 17700 | Logo | Strong
2022-12-01 | P/2021/46 | Websites | Running | N |  | 454300 | ERP | Strong
2022-12-01 | P/2021/47 | Marketing | Running | N | Client | 1203600 | Marketing | Strong
2022-12-01 | P/2021/48 | Marketing | Running | N |  | 395300 | Marketing | Strong
2022-12-01 | P/2021/49 | Websites | Running | N |  | 41300 | Single Vendor Ecommerce | Strong
2022-12-01 | P/2021/50 | Simple Apps | Running | N |  | 944000 | Multi vendor application | Strong
2022-12-01 | P/2021/51 | Websites | Running | N | Client | 30680 | Informative Website | Strong
2022-12-01 | P/2021/52 | Websites | Running | N | OIE,Client | 11210 | Informative website | Strong
2022-12-02 | P/2021/53 | Websites | Running | Y | SM | 23600 | Single vendor ecommerse | Strong
2022-12-02 | P/2021/54 | Marketing | Running | N | SM | 460200 | Video Animation | Strong
2022-12-02 | P/2021/55 | Websites | Running | N | SM | 17700 | Informative website | Strong
2022-12-02 | P/2021/56 | Complex | Running | N | SM | 182900 | Resource Allocation | Strong
2022-12-02 | P/2021/57 | Websites | Running | N |  | 30680 | Agriculture | Strong
2022-12-02 | P/2021/58 | Marketing | Running | N | Client | 171000 | 2D animated video | Strong
2022-12-02 | P/2021/59 | Marketing | Running | N | SM | 177000 | SMM | Strong
2022-12-03 | P/2021/60 | Complex | Running | N | Client | 649000 | LinkedIn Scrapper tool | Strong
2022-12-05 | P/2021/61 | Complex | Running | N | OIE | 61950 | ERP | Strong
2022-12-05 | P/2021/62 | Marketing | Running | N |  | 9440 | Marketing | Strong
2022-12-05 | P/2021/63 | Websites | Running | N | Client, SM | 118000 | Websites | Strong
2022-12-06 | P/2021/64 | Websites | Running | N | Client, OIE | 21999.92 | informative website | Strong
2022-12-06 | P/2021/65 | Websites | Running | N | Design | 23600 | single vendor ecommerce | Strong
2022-12-06 | P/2021/66 | Websites | Running | N | SM,Technical | 53100 | Websites | Strong
2022-12-06 | P/2021/67 | Marketing | Running | N |  | 311520 | Marketplace management | Strong
2022-12-07 | P/2021/68 | Complex | Running | N | OIE, Design | 300900 | LMS backend | Strong
2022-12-07 | P/2021/69 | Marketing | Running | N | Design, SM | 59000 | Marketing | Strong
2022-12-08 | P/2021/70 | Complex | Running | N |  | 944000 | multivendor e-commerce | Strong
2022-12-09 | P/2021/71 | Marketing | Delivered | N | SM | 10148 | Logo Devlopment | Strong
2022-12-09 | P/2021/72 | Websites | Running | N | Design, SM | 23600 | Informative website | Strong
2022-12-09 | P/2021/73 | Marketing | Running | N | OIE | 32450 | 2D Animation | Strong
2022-12-09 | P/2021/74 | Complex | Running | N | Client, SM | 2004820 | edtech | Strong
2022-12-09 | P/2021/75 | Websites | Running | N | Client,SM | 4130 | website maintainance | Strong
2022-12-09 | P/2021/76 | Websites | Running | N | Client, SM | 23600 | website development | Strong
2022-12-10 | P/2021/77 | Marketing | Running | N | Client | 35565 | SEO & SMM | Strong
2022-12-10 | P/2021/78 | Marketing | Running | N | OIE | 41300 | Lead generation | Strong